Terms of Reference (TOR) for an individual consultant to conduct Qualitative Data Analysis for Be in a net project 2025

- BACKGROUND AND JUSTIFICATION

Malaria remains a significant public health challenge in Sub-Saharan Africa, which bear the brunt of over 90% of the 250 million infections globally, and over half a million deaths each year. Insecticide-treated nets (ITNs) are a well-proven method to reduce the chances of malaria infection, accounting for 68% of the cases averted between 2000 and 2015. Thanks to the mass national distribution campaigns in these countries access to ITNs in many regions is high. However, there is still a significant gap between access to and use of ITNs - even when people have them, they don’t always use them. This is a complex behavioural problem. Previous studies have highlighted barriers to mosquito net use such as concerns about chemicals, difficulties in hanging nets, and discomfort during use, and lack of relative risk perception from malaria. These barriers prevent full use of ITNs even when available. This requires a behaviorally informed approach to better understand and address these issues through targeted interventions.

The study was designed to use a qualitative approach to examine current mosquito net use and related behaviours and explore facilitators and barriers to mosquito net use in Uganda. Research activities comprise interviews and household observations as well as focus groups with a diverse sample of the population in areas with access to mosquito nets. We conducted purposive sampling on geographical, socioeconomic, behavioural, and demographic characteristics to ensure breadth and diversity of study participants. The study is focusing on Sironko from Eastern and Kotido from Northern Uganda. An equivalent study is being conducted in Nigeria.

Drawing on these findings and the behavioural science literature, we designed a behavioural intervention in collaboration with key stakeholders to address the identified barriers. We conducted user testing of a low-fidelity prototype of the intervention through focus groups with potential end-users. This allowed us to seek feedback and refine the intervention to increase its acceptability and likely effectiveness. After refining the intervention, we then developed and tested a high-fidelity prototype of the intervention with potential end-users to seek further feedback.

Finally, we are piloting in a small cohort, the behavioural interventions developed to test their feasibility in a real life-setting and qualitative data is being collected.

- PURPOSE, OBJECTIVES AND SCOPE

  - Purpose of the assignment

A qualitative data analyst is needed to analyse and write up data collected from the pilot to inform performance of interventions implemented in the small cohort.

  - Specific objectives of the assignment

The aim of this study is to understand the behaviours, barriers, and facilitators affecting the use of insecticide-treated nets (ITNs) in selected areas of Uganda in order to develop a behavioural intervention to increase ITN use.

Research questions:

Primary

- Can each of the two interventions of interest be implemented in a real-life setting and is it acceptable to end users and intermediaries involved in implementation?

Secondary

- What are the obstacles that may negatively affect the adoption and retention of each of the two interventions of interest?

- What changes are required to adapt the interventions of interest and improve their feasibility and acceptability?

- What are the rates of use of ITNs in the study population?

Objectives:

- To understand the operational feasibility and acceptability of implementing two different types of behaviourally informed intervention to increase ITN use.

- To estimate the cost of implementing each of two behaviourally informed interventions to increase ITN use.

  - Scope of the assignment

Specific components include the of implementation of;

- Data cleaning

- Data analysis

- Report writing

- Dissemination of survey findings

  - Responsibilities of Malaria Consortium

- Malaria Consortium will provide the transcribed data

- Work with consultant to provide data cleaning as and when need

- Review the preliminary report

- METHODOLOGY

  - Study populations

The population studied includes adult residents of selected areas in Sironko from Eastern and Kotido from Northern Uganda. In the Exploratory phase is limited to adults who have at least one ITN in the household. The study useed purposive sampling to maximise the range and diversity of the sample, focusing on individuals from diverse demographic backgrounds to capture a comprehensive range of factors influencing ITN use. We sampled  for demographic, geographic, behavioural, and socioeconomic criteria which may influence mosquito net use including distance to closest municipality/trading centre, major economic activity, household composition, socioeconomic status, and mosquito net access, duration, and use.

  - Design

In the Pilot phase, the population studied includes adults who have been offered interventions of interest. Two solutions were developed and deployed to assess their feasibility. Each solution is implemented at a separate location and with a distinct community. Participants of the qualitative component were selected using a purposive sampling approach to maximise the range and diversity of the sample, focusing on individuals from diverse demographic backgrounds to capture a comprehensive range of factors influencing attitudes towards the intervention and ITN use. We will employ the framework developed by Bowen et al. which proposes eight areas of focus that a feasibility study may address: acceptability, demand, implementation, practicality, adaptation, integration, expansion, limited efficacy [7]. We will focus on the first six areas, while the remaining two are outside the scope of the pilot of the two interventions and should be explored in the future.

The six areas of focus investigated in the pilot phase are presented in Table 1, with their respective outcomes of interest.

Table 1

| Area of Focus | Topics to Investigate | Outcomes of Interest |
| --- | --- | --- |
| Acceptability | How the participants and implementers react to the intervention. | - Satisfaction. - Usability - Perceived appropriateness. |
| Demand | Estimated or actual use of intervention activities in the defined target group. | - Use of the intervention. - Expressed interest or intention to use. - Perceived demand. |
| Implementation | The extent, likelihood, and manner in which the intervention can be fully implemented as planned and proposed. | - Fidelity of execution. - Reach. - Success or failure of execution. - Factors affecting implementation ease or difficulty. |
| Practicality | The extent to which the intervention can be delivered when resources, time, commitment, or a combination of these are constrained in some way. | - Positive/negative effects on target population. - Ability of participants to carry out intervention activities. - Cost analysis. |
| Adaptation | The actual modifications to program contents or procedures that are made to accommodate the context and requirements of the specific format, media or population. | - Changes made or recommended to the intervention design and delivery approach. |
| Integration | The level of system change needed to integrate the new program or process into an existing infrastructure or program. | - Perceived fit with community health infrastructure. - Perceived sustainability. - Positive or negative effects on community health infrastructure. |

While all areas will be investigated for the social signaling intervention, the area of “integration” will not be explored for the Net design intervention. As the net design intervention is meant to replicate the same standard processes adopted for regular ITN mass distribution campaigns, we do not envisage observing any mechanisms of integration of a new intervention within existing delivery structures.

  - Interventions

The two interventions of interest investigated in the pilot phase are described below.

- Social signaling intervention

This intervention involves village health teams (VHT) and community leaders distributing small tokens (bracelets) to houses that are found to be using ITNs.

Step 1: We will first recruit two VHTs and one community leader to deliver this intervention to approximately 150 households in one or more contiguous locations. VHTs and community leaders will receive in-person training lasting approximately 2 hours and will receive a training leaflet containing suggested scripts to use when delivering the intervention.

Step 2: Before delivering the intervention, VHTs and community leaders will conduct community sensitisation, meeting key figures in the community to explain the intervention.

Step 3: VHTs and community leaders will then visit the 150 households to explain the intervention and ask if they want to take part. Participating households will be marked with a sticker and VHTs will make a record of households that choose to take part.

Step 4: The following week (intervention week 2) VHTs and community leaders visit a randomly selected subset of households to conduct checks to see whether ITNs are hanging in households. VHTs and community leaders will visit a subset of houses (e.g. every 10th house on their list of participating houses). Visits will take place at an appropriate time when household members are likely to be at home, such as at weekends. We will assess ITN use by looking at whether there are ITNs hanging in the household in line with current standard research methods. If either of the following are true, the house will pass the spot check:

- There is at least one ITN hanging for every two household members, or

- There is at least one ITN hanging over every sleeping space.

If the house passes the spot check, VHTs and community leaders:

- inform the person that they have passed the check, congratulate them for using ITNs and provide them with a bracelet to recognise their achievement

- inform them that they will be congratulated at a community meeting

- ask the person to remind other community members that using an ITN protects against malaria

- make a record of the household in their notebook.

If the house does not pass the spot check (if there are not enough ITNs hanging), VHTs and community leaders should politely remind household members to sleep under the ITN and explain that the VHT may return in the future for another check. VHTs and community leaders will explore the reasons why the household is not using an ITN and will provide support if possible.

Step 5: After completing the spot checks (intervention week 2 or 3), VHTs and community leaders identify an appropriate community meeting to join or organise a community meeting if there is no existing meeting. During this meeting, community leaders will present each household who has passed the spot check, explaining that they are being celebrated for using ITNs.

Step 6: This process will be repeated throughout the duration of the pilot (e.g. two further times at two weeks intervals).

Rationale

This intervention aims to reinforce intrinsic motivation to sleep in ITNs, by inscribing bracelets with positive messaging around ITN use. This symbolic association helps individuals internalise ITNs as part of a positive social identity, making sleeping under ITNs a source of pride [8]. Additionally, the visibility of bracelets and stickers will signal to community members that ITN use is a community norm [9]. There is extensive evidence for the impact of social norms on behaviour change across many domains [10].

All participants will display stickers, while VHTs will distribute bracelets to up to 30% of households. This exceeds the required ‘tipping point’ demonstrated in a landmark study, which found that groups need at least 25% of committed individuals to change group behaviour [11].

In addition, publicly acknowledging and rewarding positive behaviour with bracelets reinforces the idea that using ITNs is valued [9]. Using trusted local figures, such as community leaders and health workers, to deliver the intervention lends credibility and encourages community engagement [12].

- Net design intervention

Based on qualitative research conducted in Kotido and Sironko districts in January and March 2025 (6 focus groups), we identified that community members prefer soft and coloured (blue or green) ITNs. As a result, the preferred net intervention will involve distributing these soft, coloured ITNs to all participating households. In line with Ministry of Health’s guidance and WHO recommendations, Malaria Consortium will distribute one soft, coloured ITN for every two household members [13]. The shape of the net will also be considered and local preferences met, to the extent it is feasible to procure the desired shape. For locations where a preference for round nets is expressed, like in Karamoja, we will endeavour to distribute round nets and will investigate recipients’ response to the combined characteristic.

Rationale

Our qualitative research illustrated that many users find that standard ITNs are uncomfortable and lack intrinsic appeal. However, certain net characteristics (soft texture, blue or green colour, and in specific location the round shape) were preferred. Evidence shows that people are more likely to use products that they find appealing [9], hence our intervention aims to offer ITNs in line with users’ preferences to overcome unfavourable impressions and improve continued use.

ITN distribution will be accompanied by tailored messaging disseminated by local town announcers. These messages will emphasise the preferred characteristics of the ITNs, as well as leveraging concepts from behavioural science. Messages may draw on the idea of reciprocity, the tendency for people to behave favourably towards someone who has done something for them, by emphasising that we have listened to users’ preferences in selecting this type of ITNs [14]. Emphasising the role of people’s choice when selecting ITNs for distribution may also encourage use, as people are more likely to use a service if they feel that they played a role in its creation [15]. Similarly, people often act in a way that aligns with social norms, their understanding of what most people do [9]. Emphasising that most people like the type of ITNs being distributed will highlight that this is the social norm, encouraging use.

- DELIVERABLES:

The deliverables for the process assessment shall consist of the following:

- Inception report detailing the methodology, timelines for accomplishing the tasks and a financial proposal

- Final report not exceeding 30 pages excluding the preliminary pages and annexes. The report should cover the following key contents/outline:

- List of abbreviations and acronyms

- Operational definitions

- Executive summary (2-3 pages)

- Background inclusive of summary of TOR

- Methodology

- Findings by assessment objective / theme

- Discussion of findings

- Conclusion and recommendations

- Annexes for key additional information only

- QUALIFICATION OF CONSULTANT

The required qualifications of the lead consultant are outlined below.

- Education:

- Bachelor’s degree in social sciences and/or health related field (medicine, nursing, pharmacy, environmental health sciences, entomology, etc)

- Graduate degree (Masters or PhD) in area of public health, business administration, epidemiology and biostatistics, operations management or related field required.

- Additional training in Monitoring and Assessment, program design, and process analysis desirable but not mandatory

- Experience and knowledge:

- At least 10 years of progressive experience in conducting participatory and complex process assessments in behavioural sciences in resource constrained settings

- Previous involvement in similar assessments of scope and scale desired

- Knowledge of current malaria intervention processes and implementation arrangements

- Must be an expert in process assessment

- For ease of supervision and management, Ugandan nationals are preferred.

- Skills and competencies:

- Ability to use qualitative data analysis packages such as Nvivo, Atlas ti etc. plus office suites (Ms Word, Ms PowerPoint, Ms Excel and Ms Project packages)

- Having attention to details and being able to establish right priorities

- TIMELINE:

The process and analysis shall be carried out between 1st October and 10th November 2025

Deliverable schedule:

| Tasks | Deliverables | Time frame |
| --- | --- | --- |
| The assessment will entail the following broad tasks; - Prepare and submit an inception report detailing the methodology for data analysis. - Clean the transcriptions in preparation for analysis - Submit a preliminary survey report for review - Submit a final survey report with recommendations | An inception report detailing the methodology for data collection detailed assessment tools and Ghantt chart/timetable for activities Clean transcriptions; ready for analysis Preliminary survey report A final survey report with recommendations | By 1st october 2025 By 5th October 2025 By 20th October2025 By 10th November 2025 |

- Format for Submission of Proposals

- Expressions of interest are welcome from individual consultants. The following documentation should be submitted:

- Cover letter

- CVs of the consultant(s)

- Two sample qualitative reports

- Proposal (~2500 words in length), including suggested overview of methodology, proposed work plan, and budget (with a breakdown of costs for professional fees including salary history justification, international travel, analysis and report writing.

- Dates of availability for fieldwork.

Budget

The consultant should propose the cost of implementation of this consultancy in Uganda Shillings, stating the number of person-days’ work to be undertaken according to the level of effort. The budget should include itemized costs, communications, fees and per diem where applicable.

- 1st Installment 40% - upon submission of the Inception report with clear details of the methodology and tools

- 2nd Installment 60% - Upon submission of the final survey report

Interested parties should submit their proposals on how they will deliver the assignment and their CVs electronically to tenders@malariaconsortium.org.

World malaria report 2022. Geneva: World Health Organization; 2022. Licence: CC BY-NC-SA 3.0 IGO.

Bhatt, S., Weiss, D., Cameron, E. et al. The effect of malaria control on Plasmodium falciparum in Africa between 2000 and 2015. Nature.  2015; 526, 207–211.

The bracelet will be a simple rubber band, engraved with wording and images linked to ITN use, distributed to adults