## BOQ-of Boundary
2
STATIC HEALTH FACILITY BoQ
Drawing Number:-
Project Title : Static Health Facility Boundary Construction-Gurziwan
Specification:- Static Health Facility Boundary Construction |  |  |  | Date
Static Health Facility Boundary Construction |  |  |  | Location | Afghanistan
DESCRIPTION OF ITEMS |  |  |  | Province
|  |  |  | Planned |  |  | Revised
Item | Items Description | Size/ Specification | Unit | Qty | Unit cost USD | Total USD | Qty | Unit cost USD | Total USD | Remarks
1 | Site preparation | Site preparation and leveling (33 m x 34 m). | Lum sum | 1 |  |  | 1 | 500 | 500 | Some mountainous areas need more work for levelling.
2 | Excavations | Excavations for the fence columns as per the drawings | m3 | 9.9 |  |  | 8 | 2.5 | 20
3 | Crashed Gravel | Crushed gravels for all walkways under PCC as per the drawings (10 cm). | m3 | 26 |  |  | 24 | 20 | 480
4 | PCC (M15) | PCC for the sidewalk as per the attached drawing and guidance of relevant engineer. | m3 | 26 |  |  | 24 | 90 | 2160
5 | PCC (M15) | PCC (15) for the fence columns as per the drawings | m3 | 9.9 |  |  | 8 | 60.9114 | 487.2908
6 | GI pipe 2.5 inch for Fence | Supply and installation of GI pipe 2.5 inch, thickness= 2.5mm for the columns of the surrounding fence, each pipe should be 2.9m. | Each | 50 |  |  | 37 | 15.837 | 585.9672
7 | GI pipe 2 inch for Fence | Supply and installation of GI pipe 2.0-inch, thickness= 2.5mm for the horizontal member of the surrounding fence, each pipe should be 3m. | Each | 108 |  |  | 74 | 14.9842 | 1108.8303
8 | Wire Mesh net | Supply and installation of Wire Mesh net, the Hight of the Net should be 2m (5mmX5mm) x 3mm | M | 158 |  |  | 116 | 10.4768 | 1215.3034
9 | Shade Cloth (Health Facility Privacy Fence Cover) | Shade Cloth (Health Facility Privacy Fence Cover) with 2 meter height, 5o length should have 40 Kg of weight. | M | 158 |  |  | 116 | 5 | 580
10 | Drinking water Cooling and Heating Despenser | Supply and installation of Drinking water Cooling and Heating Despenser | PC | 2 |  |  | 2 | 600 | 1200
11 | Fire Extinguisher | Fire extinguisher (Wet Chemical, Carbon Dioxide, and ABC powder) | Set of three | 1 |  |  | 1 | 1000 | 1000
12 | Alteration of green area (garden),lown moving | Leveling and alteration of garden /platform, as per the drawings total around 165 sqare meters area. | Each | 2 |  |  | 2 | 150 | 300
13 | Precast Chairs | Supply and installation of RCC precast 3-person chairs (from 6mm steel bar) with size (120*50)cm as per the attached drawing with all necessaries. | LS | 6 |  |  |  | 6 | 0 | 0
14 | Solid waste management | Solid waste management equipment and medical dustbin and disposal bags. Total 10 Dust Bin with the capacity of 80 Liters with total 10 dozen of plactic waste bags | PC | 10 |  |  | 10 | 30 | 300
Total |  |  | USD |  |  | 0 |  |  | 9937.3918
[7 empty] | Difference | 9937.3918