## Hand Washing Station
Handwashing station for BHC-SCI-Nazine
No | Decription | Unit | Quantity | Unit price USD | Total USD | Quantity | Items Unit price USD | Total USD
1 | Site preparation and site cleaning/leveling | m2 | 4 |  |  | 4 | 5 | 20
2 | PCC (M150) for foundation, pathway, floor and under water tank with formworks and anchor bolts as per design drawings, specification and engineers’ directions and all required activities | m3 | 0.183
3 | Stone patching (thickness = 10cm based on drawings) | m3 | 0.4 |  |  | 0 | 30 | 0
4 | Brick masonry with marter 1:5 | m3 | 1.7 |  |  | 1.825 | 60 | 109.5
5 | Marble stone work | m2 | 15 |  |  | 11.035 | 10 | 110.35
6 | Supply and installation of 5 complete brass tap 1/2" along PPR pipes and with all accessories and fittings and connection with system as per design drawings, specification, and engineers’ directions and all required activities. | Set | 1 |  |  | 1 | 6.15 | 6.15
7 | Excavation for Soak pit and Saptic | m3 | 1
8 | Ring, made of PCC M150 having outer diameter of 100cm, inner diameter of 90cm and height of 40cm | pcs | 3
9 | Ring cover, made of RCC having outer diameter of 100cm, thickness of 10cm with a hole on top ( Removable ) | pcs | 1
10 | Fine sand for Soak pit and Septic | m3 | 0.256
11 | Bold stone (t = 80cm) inside of septic | m3 | 0.512
12 | Provision and installation of floor drain and connecting it with the soak pit of PVC Class B, 75mm, including fitting and all necessary accessories as per the attached drawing and guidance of the relevant engineer. | Set | 1
| Total cost of one handwash stations |  | USD |  | 0 | USD |  | 246
| Total cost of TWO handwash stations |  | USD |  | 0 | USD |  | 472

## Qaramqol (hidden)
Handwashing station for BHC-SCI
No | Decription | Unit | Quantity | Items Unit price USD | Total USD | Quantity | Items Unit price USD | Total USD
1 | Site preparation and site cleaning/leveling | m2 | 4 | 5 | 20 | 4 | 5 | 20
2 | PCC M150 (Thickness 5cm based on drawings) | m3 | 0.2 | 70 | 14 | 0.2 | 70 | 14
3 | Stone patching (thickness = 10cm based on drawings) | m3 | 0.4 | 30 | 12 | 0.4 | 30 | 12
4 | Cylindrical water tank with capacity of one cubic meter/1000 liter made of galvanized iron sheet having at least 2mm thickness. There should be two outlets having diameter of 2 inches with 2 control valves, 3m of steel pipe with diameter of 2 inches installed with 5 pieces of ¾ brass taps, one inlet and one overflow having diameter of one inch based on the attached drawings. Pedestal height should be 40cm from the ground level and made of L shape profile not iron sheet. All necessary tools such as reducers, connections and elbows are included. | Piece | 1 | 200 | 200 | 1 | 200 | 200
5 | Soak Pit for waste water | Pit | 1 | 20 | 20 | 1 | 20 | 20
| Total cost of one handwash station including one tanker |  | USD |  | 266 | USD |  | 266
[6 empty] | Planned-Implemented | 0
[6 empty] | Planned-Implemented in 6 SHF | 0

## Khwaja Sabzposh (hidden)
Handwashing station for BHC-SCI
No | Decription | Unit | Quantity | Items Unit price USD | Total USD | Quantity | Items Unit price USD | Total USD
1 | Site preparation and site cleaning/leveling | m2 | 4 | 5 | 20 | 4 | 5 | 20
2 | PCC M150 (Thickness 5cm based on drawings) | m3 | 0.2 | 70 | 14 | 0.2 | 70 | 14
3 | Stone patching (thickness = 10cm based on drawings) | m3 | 0.4 | 30 | 12 | 0.4 | 30 | 12
4 | Cylindrical water tank with capacity of one cubic meter/1000 liter made of galvanized iron sheet having at least 2mm thickness. There should be two outlets having diameter of 2 inches with 2 control valves, 3m of steel pipe with diameter of 2 inches installed with 5 pieces of ¾ brass taps, one inlet and one overflow having diameter of one inch based on the attached drawings. Pedestal height should be 40cm from the ground level and made of L shape profile not iron sheet. All necessary tools such as reducers, connections and elbows are included. | Piece | 1 | 200 | 200 | 1 | 200 | 200
5 | Soak Pit for waste water | Pit | 1 | 20 | 20 | 1 | 20 | 20
| Total cost of one handwash station including one tanker |  | USD |  | 266 | USD |  | 266
[6 empty] | Planned-Implemented | 0
[6 empty] | Planned-Implemented in 6 SHF | 0

## Pashtonkot (hidden)
Handwashing station for BHC-SCI
No | Decription | Unit | Quantity | Items Unit price USD | Total USD | Quantity | Items Unit price USD | Total USD
1 | Site preparation and site cleaning/leveling | m2 | 4 | 5 | 20 | 4 | 5 | 20
2 | PCC M150 (Thickness 5cm based on drawings) | m3 | 0.2 | 70 | 14 | 0.2 | 70 | 14
3 | Stone patching (thickness = 10cm based on drawings) | m3 | 0.4 | 30 | 12 | 0.4 | 30 | 12
4 | Cylindrical water tank with capacity of one cubic meter/1000 liter made of galvanized iron sheet having at least 2mm thickness. There should be two outlets having diameter of 2 inches with 2 control valves, 3m of steel pipe with diameter of 2 inches installed with 5 pieces of ¾ brass taps, one inlet and one overflow having diameter of one inch based on the attached drawings. Pedestal height should be 40cm from the ground level and made of L shape profile not iron sheet. All necessary tools such as reducers, connections and elbows are included. | Piece | 1 | 200 | 200 | 1 | 200 | 200
5 | Soak Pit for waste water | Pit | 1 | 20 | 20 | 1 | 20 | 20
| Total cost of one handwash station including one tanker |  | USD |  | 266 | USD |  | 266
[6 empty] | Planned-Implemented | 0
[6 empty] | Planned-Implemented in 6 SHF | 0

## Belchiragh (hidden)
Handwashing station for BHC-SCI
No | Decription | Unit | Quantity | Items Unit price USD | Total USD | Quantity | Items Unit price USD | Total USD
1 | Site preparation and site cleaning/leveling | m2 | 4 | 5 | 20 | 4 | 5 | 20
2 | PCC M150 (Thickness 5cm based on drawings) | m3 | 0.2 | 70 | 14 | 0.2 | 70 | 14
3 | Stone patching (thickness = 10cm based on drawings) | m3 | 0.4 | 30 | 12 | 0.4 | 30 | 12
4 | Cylindrical water tank with capacity of one cubic meter/1000 liter made of galvanized iron sheet having at least 2mm thickness. There should be two outlets having diameter of 2 inches with 2 control valves, 3m of steel pipe with diameter of 2 inches installed with 5 pieces of ¾ brass taps, one inlet and one overflow having diameter of one inch based on the attached drawings. Pedestal height should be 40cm from the ground level and made of L shape profile not iron sheet. All necessary tools such as reducers, connections and elbows are included. | Piece | 1 | 200 | 200 | 1 | 200 | 200
5 | Soak Pit for waste water | Pit | 1 | 20 | 20 | 1 | 20 | 20
| Total cost of one handwash station including one tanker |  | USD |  | 266 | USD |  | 266
[6 empty] | Planned-Implemented | 0
[6 empty] | Planned-Implemented in 6 SHF | 0

## Qaisar (hidden)
Handwashing station for BHC-SCI
No | Decription | Unit | Quantity | Items Unit price USD | Total USD | Quantity | Items Unit price USD | Total USD
1 | Site preparation and site cleaning/leveling | m2 | 4 | 5 | 20 | 4 | 5 | 20
2 | PCC M150 (Thickness 5cm based on drawings) | m3 | 0.2 | 70 | 14 | 0.2 | 70 | 14
3 | Stone patching (thickness = 10cm based on drawings) | m3 | 0.4 | 30 | 12 | 0.4 | 30 | 12
4 | Cylindrical water tank with capacity of one cubic meter/1000 liter made of galvanized iron sheet having at least 2mm thickness. There should be two outlets having diameter of 2 inches with 2 control valves, 3m of steel pipe with diameter of 2 inches installed with 5 pieces of ¾ brass taps, one inlet and one overflow having diameter of one inch based on the attached drawings. Pedestal height should be 40cm from the ground level and made of L shape profile not iron sheet. All necessary tools such as reducers, connections and elbows are included. | Piece | 1 | 200 | 200 | 1 | 200 | 200
5 | Soak Pit for waste water | Pit | 1 | 20 | 20 | 1 | 20 | 20
| Total cost of one handwash station including one tanker |  | USD |  | 266 | USD |  | 266
[6 empty] | Planned-Implemented | 0
[6 empty] | Planned-Implemented in 6 SHF | 0

## Total (hidden)
Handwashing station for BHC-SCI
No | Decription | Unit | Quantity | Items Unit price USD | Total USD | Quantity | Items Unit price USD | Total USD | Type
1 | Site preparation and site cleaning/leveling | m2 |  |  | 100 |  |  | 120 | Procurement
2 | PCC M150 (Thickness 5cm based on drawings) | m3 |  |  | #REF! |  |  | #REF! | Procurement
3 | Stone patching (thickness = 10cm based on drawings) | m3 |  |  | 60 |  |  | 60 | Procurement
4 | Cylindrical water tank with capacity of one cubic meter/1000 liter made of galvanized iron sheet having at least 2mm thickness. There should be two outlets having diameter of 2 inches with 2 control valves, 3m of steel pipe with diameter of 2 inches installed with 5 pieces of ¾ brass taps, one inlet and one overflow having diameter of one inch based on the attached drawings. Pedestal height should be 40cm from the ground level and made of L shape profile not iron sheet. All necessary tools such as reducers, connections and elbows are included. | Piece |  |  | #REF! |  |  | #REF! | Procurement
5 | Soak Pit for waste water | Pit |  |  | #REF! | 1 | 20 | #REF! | Procurement
| Total cost of one handwash station including one tanker |  | USD |  | #REF! | USD |  | #REF!
[6 empty] | Planned-Implemented | #REF!
[6 empty] | Planned-Implemented in 6 SHF | #REF!