Terms of Reference for the final external evaluation of “Integrated life-saving and life-sustaining support for vulnerable communities and out of school children in Wardak and Samangan” project

Implemented in Maidan Wardak and Samangan provinces of Afghanistan

Project implementation period 01/05/2023– 30/09/2026

Evaluation expected to be conducted from 02/08/2026 to 18/09/2026

Terms of Reference for the final external evaluation of “Integrated life-saving and life-sustaining support for vulnerable communities and out of school children in Wardak and Samangan” project

Implemented in Maidan Wardak and Samangan provinces of Afghanistan

Project implementation period 01/05/2023– 30/09/2026

Evaluation expected to be conducted from 02/08/2026 to 18/09/2026

Table of contents

1.	Background	2

1.1.	Our Profile	2

Project Overview	3

2.	Objective of the project	3

2.1.	Overall objective:	4

2.2.	Specific Objective:	4

3.	Objective and scope of the Evaluation	4

3.1.	Objectives of the evaluation	4

3.2.	Scope of the evaluation	5

4.	Key evaluation questions	5

4.1.	Relevance	5

4.2.	Coherence	6

4.3.	Effectiveness	6

4.4.	Efficiency	6

4.5.	Impact	7

4.6.	Sustainability	7

5.	Methodology	7

5.1.	Data source and Type	7

5.2.	Method of data analysis	7

6.	Specific tasks	7

7.	Expected deliverables	8

8.	Main Points in Evaluation Report	8

9.	Duration	9

10.	Logistics	9

11.	Qualifications and requirements	9

12.	Evaluation Team Composition	10

| Period of assignment | August-September 2026 |
| --- | --- |
| Country | Afghanistan |
| Duty station | Kabul |
| Period under review | 01/05/2023-30/09/2026 |
| Donor | ECHO |

# Background

## Our Profile

People in Need (PIN) is a Czech organisation established in 1992, currently working in around 40 countries on human rights and humanitarian aid. Globally, PIN is recognised as a leading actor in Education in Emergencies and actively contributes to international coordination mechanisms and humanitarian clusters, including education, food security, nutrition, shelter, and WASH. In Afghanistan, PIN has been operating since 2001, delivering humanitarian and development assistance to communities affected by conflict, economic crisis, and natural disasters. Over the years, PIN has established itself as a trusted and experienced actor, with strong acceptance among local communities, authorities, and stakeholders, enabling access to some of the most vulnerable and hard-to-reach populations.

Throughout its presence in the country, PIN has supported over 850,000 people across multiple regions. The organisation has remained operational through periods of significant political and social change, continuing to provide life-saving and resilience-building assistance to more than 250,000 individuals in recent years. It works in key sectors including food security and livelihoods, education in emergencies, water, sanitation and hygiene (WASH), and protection.

PIN has a strong operational footprint in both Wardak and Samangan provinces. In Wardak, the organisation has been active since 2022, delivering integrated humanitarian support to nearly 150,000 vulnerable individuals. Samangan represents one of PIN’s long-standing areas of intervention, with programming dating back to 2003, allowing the organisation to maintain strong community relationships and contextual knowledge.

PIN operates through its main office in Kabul, supported by regional and field offices across the country, and actively participates in national and sub-national humanitarian coordination mechanism.

## Project Overview

The project, “Integrated Life-Saving and Life-Sustaining Support for Vulnerable Communities and Out-of-School Children in Wardak and Samangan Provinces,” is funded by ECHO and implemented by PIN in partnership with SADA, in Afghanistan. The intervention targets crisis-affected communities in Nerkh and Maidan Shar District of Wardak Province and the districts of Hazrat e Sultan, Dare Suf Bala and Dare Suf Payin in Samangan Province. This project focuses on addressing immediate humanitarian needs while supporting long-term resilience and ensuring that vulnerable children can access safe and quality education.

In response to the high number of out-of-school children in the targeted areas, the project prioritises access to structured learning opportunities through the establishment of community-based classes in remote villages of Samangan and Wardak provinces. These learning spaces provide safe and child-friendly environments where children continue their education, strengthen foundational literacy and numeracy skills, and receive psychosocial support to address the impacts of conflict, displacement, and prolonged educational disruption.

This education intervention also includes teacher recruitment and training, provision of teaching and learning materials, psychosocial support activities, and community engagement initiatives. These activities are designed to improve teaching quality, encourage attendance, and strengthen retention and transition of children into the formal education system. To further support safe learning environments, the project rehabilitates sanitation facilities, installs handwashing stations, and promotes hygiene awareness in schools and communities.

Alongside the education response, the project provides Cash Assistance to highly vulnerable households, particularly (1) during the winter season when income opportunities decline and basic needs become more difficult to meet, and (2) during harvesting season when income opportunities prevent children to go to school. This support helps households cope with food insecurity and reduces negative coping mechanisms that may affect children’s ability to remain in school.

# Objective of the project

To achieve the aim of the project strategy was formulated on following key areas; overall objective, outcome and outputs:

## Overall objective:

Crisis-affected communities are better able to withstand seasonal and sudden shocks, while their children access education, learn effectively, and achieve improved well-being.

## Specific Objective:

Crisis-affected out-of-school children and their vulnerable households in target communities meet their seasonal basic life-saving needs and gain access to safe, quality formal education.

Partner:  Social Association for Development of Afghanistan (SADA)

Intervention areas: Central region (Nerkh and Maidan Shar districts of Maidan Wardak province), North region (Dare Suf Balad, Dare Suf Payin and Hazrat-e-Sultan districts of Samangan province), Afghanistan.

Target groups in the project:

Direct beneficiaries of the project

- 150 teachers

- 5,250 out of school children benefitting from CBE classes

- 75 homework club volunteers

- 11,582 hub school children who benefit from rehabilitation of their school

- 450 School Management Shura members

- 1,423 community members (households) who received MPCA

- 1,000 families (households) who received Cash for Education

# Objective and scope of the Evaluation

## Objectives of the evaluation

The evaluation will address the following objectives.

- To provide a comprehensive assessment of the project through OECD/DAC evaluation criteria of relevance, efficiency, effectiveness, coherence, impact and sustainability.

- To provide lessons learned and recommendations for future programming in similar contexts.

The overall objective of the evaluation is to assess the achievements of the EiE, Cash Assistance, and WASH activities in relation to the objective of supporting crisis-affected out-of-school children and their vulnerable households to meet their seasonal basic life-saving needs and gain access to safe, quality formal education, track lesson learned and provide recommendation for management.

Specific Objectives of the Evaluation

The evaluation will address the following specific objectives:

- To evaluate the achievements of the intervention in relation to the goal, objectives and results defined in Action proposal and establish the relevance of the project design and implementation.

- To collect and analyse data to determine if and how the intervention achieved its intended outcomes and met the needs of the beneficiaries.

- To evaluate overall effectiveness, sustainability and relevance of the Action activities and outcomes  to improve children’s access to quality and continuous education (including transitioning to formal education); giving specific attention to whether education, WASH and Cash Assistance activities were delivered in safe, inclusive and child-friendly environments, and whether safeguarding measures — including safe programming standards, codes of conduct, and referral pathways to child protection services — were consistently applied ; as well as to identify external and Action related factors (if any) limiting the achievements of the programme.

- To provide recommendations to project stakeholders based on identified best practices and areas for improvement, strengths, and challenges in the design of Action activities, and their implementation, coordination, partnership and monitoring, including the integration of child protection and safeguarding standards across all components and partners, to improve their efficiency and usefulness for PIN’s interventions in Afghanistan.

## Scope of the evaluation

The scope of the evaluation will cover the full project period and all activities implemented by PIN (Cash Assistance) and by SADA (EiE and WASH). It encompasses two primary components: the overall effectiveness and relevance of project activities and an evaluation of the partners’ performance.

- The evaluation will assess the extent to which project implementation remained consistent with the initial needs assessment, project design, and approved work plan, and whether activities were aligned with the Action’s overall and specific objectives. It will examine the effectiveness and efficiency of the intervention by assessing whether project inputs were converted into planned outputs and outcomes in terms of both quality and quantity, and whether the expected results and impacts were achieved. In particular, it will evaluate the effects of the Action on learning outcomes and school protective environments, access to sanitation, households' resilience, negative coping mechanisms, overall effectiveness, and relevance of the project activities. It will also review compliance with key donor requirements and agreed objectives. Particular attention will be paid to the extent to which the project addressed the specific needs of persons with disabilities and promoted inclusive access to services. Based on the findings, the evaluation will provide practical recommendations regarding whether and how the project approach, implementation modalities, or strategic orientation should be adapted for future interventions, taking into account the evolving context in the areas of operation.

- Partner’s performance and PIN’s partnership approach: the evaluation will also evaluate the partner’s performance, its achievement of targets, PIN’s progress in following the Capacity Building Plan, potential gaps, and further needs for capacity strengthening. The final evaluation will also look at the partnership to identify strengths and weaknesses of the work done by PIN to support the partner and to identify if and where PIN's partnership approach can be improved

# Methodology

## Data source and Type

The final evaluation will adopt a mixed-methods approach, utilizing both primary and secondary data sources to assess the relevance, coherence, effectiveness, efficiency, impact, and sustainability of the project interventions.

Primary data will be collected through Focus Group Discussions (FGDs), Key Informant Interviews (KIIs), Interview with project beneficiaries and direct field observations. Primary data collection will target key stakeholder groups, including children enrolled in Community-Based Education (CBE) classes, parents and caregivers, teachers, School Management Shuras (SMSs), homework club volunteers, community representatives including community leaders, Hub schools representatives, Cash Assistance beneficiaries, partner organization staff, local authorities, and project implementation teams. These methods will provide first-hand qualitative information on beneficiaries’ experiences, perceptions of project outcomes, changes in access to education and basic services, effectiveness of assistances provided, and the sustainability of project achievements.

Secondary data will be obtained through a comprehensive desk review of project documentation and existing monitoring data. This will include project proposals, logical frameworks, monitoring reports, post-distribution monitoring (PDM) reports, MEAL databases, activity reports, training records, attendance records, donor reports, and other relevant project documents. Secondary data will be used to verify findings, assess progress against planned indicators and targets, and provide contextual information on project implementation and achievements.

## Method of data analysis

The data collected from primary and secondary sources will be analysed by using descriptive statistics methods. Qualitative data collected through Focus Group Discussions (FGDs), Key Informant Interviews (KIIs), direct observations, will be entered into designated excel template for further data cleaning and analyzation. Qualitative data will tabulate to assess the level of achievement of project objectives and/or long-term impact, provision of recommendations for the management to decide about future programming.

The collected information will be organized and analyzed according to key evaluation themes and criteria to identify common patterns, stakeholder perceptions, lessons learned, best practices, challenges, and factors influencing project performance and sustainability. The findings will be synthesized in a comprehensive final evaluation report, providing an evidence-based assessment of project achievements, outcomes, and long-term impacts, as well as actionable conclusions and recommendations to inform future programming and strategic decision-making.

Key evaluation questions

The final evaluation will be based on the following evaluation questions:

## Relevance

- To what extent activities implemented are relevant to the context and the needs of the affected population? How well did the Action adapt to educational needs along the standards identified by the local education department/committees/ or clusters?

- To what extent did the Action’s activities meet the core educational needs of the beneficiaries? What can be done in terms of approach and design of activities to make them more appropriate to the needs of communities and children, education staff and families benefitting from the provided support and services?

- To what extent was the design of the Cash Assistance activities adapted to answer to the needs of the targeted communities? And to promote class attendance?

- To what extent did PIN’s capacity strengthening approach respond to the partner’s actual institutional and technical gaps?

- Were the assumptions, risks, and mitigation measures identified in the project design relevant to the Action and evolving context?

## Coherence

- To what extent was the intervention aligned with national policies, humanitarian response plans, and cluster (education) strategies?

- To what extent did the project EiE and WASH results contribute to supporting the national schooling system?

- How well were the EiE, Rehabilitation, WASH and Cash Assistance components integrated within one another?

- To what extent were cross-cutting issues (environment, protection, inclusion...) integrated consistently across sectors?

- Did the project promote equitable partnership practices?

## Effectiveness

- To what extent have the overall design of the Action components been effective in achieving the access to quality education and learning outcomes for the targeted children in relation to the defined standards?

- What were the major internal and external factors influencing the achievement or non-achievement of project objectives?

- How effective was the project in achieving the project’s objectives?

- Has PIN monitoring mechanism been effective to inform programme progress and decision making? And in answering beneficiaries' inquiries and feedback?

- How effectively did the project identify and address the specific needs, risks, and barriers faced by women and girls, as well as children with disabilities, in the Afghan context, and how were these reflected in project design, implementation, and adaptation?

- Did the project strengthen the partner’s ability to design, implement, monitor, and report humanitarian interventions?

- If any mitigation measures were applied during project implementation, were they effective to face the risk that manifested?

## Efficiency

- Were the Actions activities time-efficient and cost-effective?

- Are the human resources dedicated to the project sufficient for project efficiency?

- Which capacity-building modalities provided the greatest value for effort and cost and why?

## Impact

- What are the measurable changes brought due to the project intervention in the life of target beneficiaries?

- What are the barriers that have limited its success?

- To what extent did the project improve well-being, dignity, resilience, and coping capacity of the children, their family and their community?

- How did the project address barriers to girls' education and what evidence is there of change in enrolment, retention or learning outcomes disaggregated by sex?

- To what extent did the intervention strengthen community resilience to future shocks?

- Did the project generate any negative effects (environment, economy, security, harm to affected population, etc.)? If not, how did the project Action mitigate the risks of generating some?

## Sustainability

- What are the possibilities to sustain the interventions in terms of children’s access to quality and continuous formal education and what can be done to ensure it? Considering reducing funds, exiting from schools/centers etc.

- What are the challenges that could create hindrances in sustaining the programme outcomes?

- To what extent are strengthened partner capacities likely to be retained over time?

## Cash for Education pilot

- What are the evidences generated by this modality?

- What are the positive and negative impacts of this practice? Both at the children level, household level, and community level.

- What are the lessons learnt and ways forward to better adapt this practice to the Afghan context?

- What are the possibilities to make its impact sustainable?

# Specific tasks

The evaluator will be required to undertake the following tasks:

- Review of the project documentation

- Review of MEAL documentation inclusive of the project’s results framework

- Development of an inception report and data collection tools, to be verified and agreed upon with PIN

- Data collection in the field

- Meeting with project staff, beneficiaries and relevant stakeholders

- Submission of preliminary findings and conduction of a verification workshop

- Preparation of the evaluation documents (draft and final evaluation reports inclusive of recommendations and lessons learnt for future programming capacity)

- Incorporating stakeholders’ feedback in draft report and final report submission

# Main Points in Evaluation Report

The evaluation report will have following structure:

- Executive summary: Summary of the evaluation, with particular emphasis on the main findings, conclusions, lessons learned and recommendations.

- Introduction: Description of the evaluated intervention, its logic, history, organisation and stakeholders. Presentation of the evaluation’s purpose and questions.

- Methodology: Description of the sampling strategy and methods used for data collection; description of the limitations.

- Findings: Factual evidence relevant to the questions asked by the evaluation and interpretations of such evidence (answered evaluation questions).

- Problems and needs (relevance)

- Achievement of purpose (effectiveness)

- Sound management and value of money(efficiency)

- Achievement of wider effects(impacts)

- Sustainability of achieved results

- Cash for Education pilot evidence and learning generation

- Capacity building and partnership

- Monitoring and Evaluation process

- Conclusions and overall assessment: Assessments of intervention results and performance against given evaluation criteria and standards of performance.

- Recommendations: Specific and actionable proposals regarding improvements of the project or management addressed to the client of the evaluation or other intended users.

- Annexes:  2 pager Lesson Larned document and evaluation brief

The evaluation report Executive summary should not exceed the limit of 3 pages, and the remaining parts of the report should not exceed 30 pages (excluding annexes).

# Duration

The final evaluation will be conducted during the month of XXX, within & after the termination of the project.

Please refer to the tentative schedule below.

| ACTIVITIES | TIMING | COMPLETION DATE |
| --- | --- | --- |
| Preparation (Inception Report) | One week |  |
| Field visit (including data collection) | Two weeks |  |
| Draft of the outputs | Two weeks |  |
| PIN revision of the outputs | One week |  |
| Integration of PIN feedback and finalization of the outputs | One week |  |

# Qualifications and requirements

Essential:

- Relevant subject matter knowledge and experience: knowledge and experience required on conducting research with children, the education sector, disability and gender to ensure that the evaluation design and research methods are as relevant and meaningful as possible given the aims and objectives of the project and the context in which it is being delivered

- Country experience: it is particularly important that the team has the appropriate country knowledge /experience and language proficiency required to conduct the research required.

- Proven experience and knowledge of conducting quantitative and qualitative research;

- Excellent analytical skills;

- Significant practical experience in report writing and formulation of recommendations;

- Excellent spoken and written English.

- Understanding of key safeguarding issues relevant to the assignment and experience of designing and implementing M&E activities that ensure the safety and rights of vulnerable participants are protected.

Preferred:

- Experience evaluating ECHO-funded projects;

- Previous experience with results‐based monitoring and evaluation methodologies;

- Dari/pashto language will be considered an advantage.

# Budget

The estimated budget for this work is 30,000 USD. This budget should cover the data collection, analysis and reporting. This budget is inclusive of all costs covering team member costs, travel, research costs and any other costs associated the completion of the work. Bidders are required to organise and fund their own duty of care arrangements as required.

Bidders are required to provide a fully costed proposal in the form of a price schedule that as a minimum should include:

    - Sub-total of fees for the delivery of any task or deliverable.

    - Sub-total for number of days per partner organisation (as applicable).

    - Expenses and overheads broken down by the project cost categories specified in Appendix X.

    - Reasonable adjustment costs.

    - Total costs before and after any taxes that are applicable.

# Application Process

The deadline for submission of applications is XXX.

The length of the technical proposal should not exceed 10 pages using Calibri font, size 11.

•	Contents of application package:

•	Organization overview:

-	Valid registration certificate,

-	Organizational profile including the structure of governing bodies, and areas of expertise

List of past experience on relevant topic developed by bidder’s organization over the past 5 years: experience must be related to evaluation either in (1) Education, (2) Afghanistan, and/or (3) on ECHO projects, and must be relatively recent

-	Up to three sample of past reports

-	For XXXX organizations: VAT number, tax clearance letter renewal, past two years’ audit reports

•	Technical proposal including:

-	Evaluation design

-	Data collection approach to evaluate each outcome

-	Detailed Workplan with timeline

-	Risk management plan

-	Quality assurance plan

-	CVs of the Evaluation Team, clearly stating their roles and responsibilities for this evaluation, relevant technical expertise, and practical experience

•	Financial proposal

-	Budget including: data collection, analysis and reporting, inclusive of all costs covering team member costs, travel, research costs and any other costs associated the completion of the work including where required costs for reasonable adjustment

•	Two references

•	Contact details

Applications should be delivered to Procurement office of PIN by email to @peopleinneed.cz.

Annex: Project Document