TERMS OF REFERENCE FOR FORMATIVE ASSESSMENT AND IMPLEMENTATION DESIGN FOR THE DIFFERENTIATED SEASONAL MALARIA CHEMOPREVENTION (SMC) DELIVERY MODELS IN NIGERIA (FCT, KEBBI & BORNO)

| Reference number |  | Output | Differentiated SMC Delivery Models |
| --- | --- | --- | --- |
| Date of draft | August 4, 2026 | Technical lead(s) | Dr Kolawole Maxwell |
| Date of final | August 11, 2026 | Period of assignment | August 2026-January 2027 |
| Responsible person | Michael Ekholuenetale | Status | Final |

BACKGROUND:

Established in 2003, Malaria Consortium (MC) is one of the world's leading non-profit organizations dedicated to improving health and saving lives in communities affected by malaria and related inequities in Africa and Southeast Asia. With over 20 years of proven impact, the organization works with governments, academic institutions, local and international organizations to deliver scalable, locally led health solutions grounded in research and evidence to strengthen health systems, inform policy and derive sustainable impact through strategic partnerships and organizational excellence.

Malaria Consortium is currently implementing Phase 1 of The Gates Foundation funded project Differentiated Delivery Models for seasonal malaria chemoprevention (SMC) which is taking place from July 2026 to January 2027. This Phase 1 formative assessment consists of four components designed to assess the feasibility, acceptability, and operational and financial implications of differentiated SMC delivery models across a range of implementation contexts and target populations AMAC - FCT, Suru LGA - Kebbi State & Jere LGA - Borno State. This phase will lead to identifying and defining the differentiated SMC delivery models suitable for proof-of-concept testing, and will support the generation of the evidence and design parameters required to inform a Phase 2 trial of those models. This Phase 1 consultancy will be responsible for implementing key activities within formative assessment Components 2 (qualitative inquiry to explore feasibility and acceptability) & 3 (rapid human-centered behavioral design).

PRIMARY ROLE:

The primary role of the consultant/s is to deliver on Components 2 (qualitative inquiry to explore feasibility and acceptability) across AMAC - FCT, Suru LGA - Kebbi State & Jere LGA - Borno State & 3 (rapid human-centered behavioral design).

Population Selection Rationale

The formative assessment will be conducted in three targets underserved and operationally challenging contexts within the country. These population groups are being selected from a longer list of potential contexts, which include, but are not limited to, remote rural communities, urban poor populations, nomadic or pastoralist groups, populations affected by conflict or insecurity, migrant and mobile populations, and other relevant underserved groups identified.

Operational contexts have been ranked by their suitability for examining differentiated SMC delivery, and a lead LGA selected for each from the 2026 consolidated microplan, cross-checked against referenceable data — IOM DTM displacement figures, flood and access reporting, and security reporting — and against administrative and end-of-cycle (survey) coverage. Three contexts have been selected:

- Urban — Abuja Municipal (AMAC), FCT. The largest SMC target in the dataset (~491,000 children). Ward-level profiling from the FCT Department of Mass Housing confirms a predominantly urban population concentrated in the central wards. End-of-cycle survey coverage is low (63% rising to 79%), marking a genuine urban delivery gap behind administrative coverage near 100%.

- Mobile / nomadic — Suru, Kebbi State. The highest nomadic-settlement share (54%). Its end-of-cycle survey coverage (77.5%) is the lowest of the selected LGAs, consistent with mobility disrupting cycle completion. Sits in an SMC-ORSZ state; access to be confirmed against the security overlay.

- Displaced — Jere, Borno State. The largest internally displaced persons (IDP) population in north-east Nigeria (237,947; 54% in camps, IOM DTM Round 52) and the only high-burden Borno displacement LGA accessible for implementation — a distinct, camp-based delivery context.

SCOPE OF WORK:

This formative assessment for this consultancy consists of three interrelated components: feasibility and acceptability research and rapid human centred design. The geography, method and expected knowledge output for each formative assessment component are summarised in Table 1.

Table 1: Overview of the formative assessment components

| Component | Geography | Method | Knowledge output |
| --- | --- | --- | --- |
| - Feasibility and acceptability | - Urban — Abuja Municipal (AMAC), FCT - Mobile / nomadic — Suru, Kebbi State - Displaced — Jere, Borno State | - KIIs (national and state / LGA MoH) - FGDs (Supervisors, Distributors, caregivers –male and female) | Acceptability, barriers and enablers identified for the delivery models with considerations based on the socio-ecological model |
| - Rapid human centred design | - Urban — Abuja Municipal (AMAC), FCT - Mobile / nomadic — Suru, Kebbi State - Displaced — Jere, Borno State | - Human Centred Design incorporating participatory human centred design sessions in each location with: - Caregivers (male and female) - Community distributors, supervisors | Minimum viable support package |

The knowledge outputs from these components will be used to define a set of differentiated SMC delivery models suitable for proof-of-concept testing, including their target populations, implementation contexts, and minimum support packages. These models will be refined and validated through national- and sub-national-level stakeholders’ engagement, and used to establish key design parameters for a phase 2 proof-of-concept trial.

Feasibility and acceptability

Data collection/qualitative interviews

This component will take place in Nigeria, engaging stakeholders at national, implementation, and community levels through key informant interviews and focus group discussions, to understand the feasibility and acceptability of differentiated SMC delivery among key target populations in AMAC - FCT, Suru LGA - Kebbi State & Jere LGA - Borno State.

Key informant interviews will be conducted with national-level stakeholders, including National Malaria Elimination Programme (NMEP), other relevant government bodies, implementing partners, and other national-level figures with direct involvement in SMC planning, delivery, and decision-making.

Focus group discussions will take place within key target populations AMAC - FCT, Suru LGA - Kebbi State & Jere LGA - Borno State, at both implementation level (community distributors and supervisors) and community level (caregivers/community representatives).

Sampling for qualitative interviews

Information-rich individuals involved in the planning, management, and/or delivery of SMC will be interviewed at national level in Nigeria. These individuals will be identified through a pre-determined participation programme, consisting of pre-defined job titles associated with SMC planning and decision-making at national level, including NMEP staff, other relevant government bodies, and implementing partners. We will conduct 10 interviews at national level, with flexibility in line with data saturation. Data saturation will be achieved when the operational and decision-making mechanisms relevant to differentiated SMC delivery have been exhaustively discussed to the point of repetition.

Caregivers will be purposively sampled through community entry points (e.g. community distributors, health facility staff, community leaders), and will include caregivers of SMC-eligible children resident in the target population area since at least six months. Sampling will include caregivers within the target population who have and have not taken up SMC through the current delivery model, to capture a range of experience relevant to feasibility and acceptability. FGDs will be split by gender, with separate groups for male and female caregivers. In addition, community distributors and supervisors will be recruited at implementation level within the key target populations. These individuals will be identified with support from local SMC implementation teams. We will conduct eight FGDs per target population, two with community distributors; two with supervisors, two with male caregivers; two with female caregivers - totalling eight FGDs per population, with 6-8 participants per FGD (up to 48 participants).

Selection of participants for the differentiated SMC delivery models design

Participants will be drawn primarily from Component 2, using the consent to be recontacted recorded at that stage, with a proportion recruited afresh to test whether the propositions make sense to people meeting them for the first time. Each workshop will comprise four separate groups of six participants each: female caregivers, male caregivers, community distributors, and supervisors. This will give a maximum of 24 participants per workshop per population. The same participants will be invited to the second workshops. Caregiver groups will additionally consider who authorises participation, administers doses, stores the medicine and remembers the next cycle. Recruitment will take account of the design activities, which ask participants to work through operational sequences and propose solutions; materials and facilitation will be designed so that no activity requires reading or writing. A maximum of ten programme and policy stakeholders in Nigeria will take part in the final session, giving a maximum of 30 participants for the three populations. The sampling for the feasibility is summarised in Table 2.

Table 2: Summary of participant sampling for Component 2 (feasibility and acceptability)

| Level | Participant group | Method | No. interviews/FGDs | Total No. participants |
| --- | --- | --- | --- | --- |
| National | SMC planning/management /delivery stakeholders (NMCP, government bodies, implementing partners) | KII, identified via pre-determined participation programme | Up to 10 interviews | 10 |
| Implementation | Community distributors | FGD, identified with support from local SMC implementation teams | 2 FGDs per target population | Up to 48 |
|  | Supervisors | FGD, identified with support from local SMC implementation teams | 2 FGDs per target population | Up to 48 |
| Community | Caregivers (male) | FGD, purposively sampled via community entry points | 2 FGD per target population | Up to 48 |
|  | Caregivers (female) | FGD, purposively sampled via community entry points | 2 FGD per target population | Up to 48 |

Data analysis for the qualitative interviews

To facilitate refinements and delivery of the subsequent rapid human centred design, initial analysis will follow a rapid qualitative assessment approach, utilising a table-based method structured around RREAL Summary Sheets to rapidly synthesis emerging findings during the field work.

Subsequently, all data will be transcribed verbatim and, where required, translated into English. Thematic analysis of dataset will be used to inductively and deductively identify themes and sub-themes. Distinct analysis will be conducted for each population groups targeted in Nigeria, with analysis by delivery model explored where the data allows.

Data analysis for the differentiated SMC delivery models design

Rapid framework analysis will be used. A matrix prepared in advance from the design specification will have rows for the behaviours, barriers and resources identified, and columns for each model, target population and participant group. Facilitators will complete structured debriefs within 24 hours of each workshop, and workshop outputs will be photographed and charted into the matrix.

Charting will be done in two stages: material from the first workshops will shape prototyping and the provisional pathway required to inform the subsequent cost optimisation and scenario modelling, with the second workshops and the final session added to produce the complete model refinements and behavioural support package.

Expected output from the qualitative interviews

Findings reports will be generated for Nigeria, presenting the themes and sub-themes that emerged in relation to feasibility and acceptability of differentiated SMC delivery among each target populations in Nigeria.

These findings will directly inform Component 3, rapid human centred design, by identifying key barriers, facilitators, and preferences relevant to delivery model design.

Expected output from the differentiated SMC delivery models design workshop

The rapid human centred design will produce a specified operational pathway for each model and target population, with the support package that enables it and the resource schedule needed for costing, together with the prototypes and a record of what programme and policy stakeholders said would need to change. Findings will be triangulated with the other components to inform the Phase 2 design parameters.

SPECIFIC ACTIVITIES:

- Adhering to all protocols, guides and procedures outlined by Malaria Consortium, the consultant will:

- Organise and conduct key informant interviews (KIIs) with stakeholders working in SMC at the national and state/LGA level.

- Organise and conduct focus group discussions (FGDs) with SMC staff (supervisors and community distributors), as well as community members (caregivers/community representatives) in the identified locations and population groups.

- Lead the participant information and informed consent process for all study participants.

- Ensure secure storage and management of all study data and adherence to approved ethical, confidentiality, and data protection requirements throughout the consultancy.

- Ensure transcription and, where needed, translation of all KIIs and FGDs into English including check for quality assurance.

- Develop and refine a qualitative codebook, ensure inter-coder reliability through quality assurance processes, code qualitative datasets, and conduct thematic analysis of the data.

- Organise and lead participatory behavioral co-design workshops with caregivers and community distributors to inform a minimum viable support package in the identified locations and population groups.

- Write the technical reports based on the findings from Component 1 and 2 activities.

EXPECTED OUTPUTS:

- Transcribed and translated qualitative datasets (Component 2).

- Final codebook/coding framework used for qualitative analysis (Component 2).

- Written report of the findings from the qualitative inquiry into the feasibility and acceptability of differentiated SMC delivery models (Component 2).

- Written report of the findings from the behavioural design exploration, including the minimum viable support package (Component 3).

REPORTING:

The consultant(s) will work in close collaboration with Malaria Consortium Project team and report directly to the Country Research & Knowledge Management Specialist. Progress updates must be provided on a weekly basis throughout the duration of the consultancy, including the submission of draft outputs and all other materials to Malaria Consortium staff upon request.

The consultant(s) will securely transfer study data and associated materials to Malaria Consortium on a regular basis throughout the consultancy (at a minimum on a weekly basis, or more frequently as agreed), to ensure secure storage, oversight, and continuity of access to study data.

The consultant(s) will be responsible for securely transferring all study data to Malaria Consortium at the end of the contract period. This includes, but is not limited to, KII and FGD recordings, transcripts, translations, consent forms, field notes, codebook, and analysis files. No study data may be retained by the consultant(s) following completion of the contract, nor may study data be shared with any individual or organisation outside the approved study team within Malaria Consortium at any time. All study data remain the property of Malaria Consortium.

EXPECTED EXPERIENCE AND SKILLS:

- Proven track record of experience in qualitative research methods, including firsthand experience facilitating interviews and focus group discussions with both national- and community-level participants

- Experience using qualitative data analysis software (MAXQDA or N’vivo)

- Proven track record of experience developing and facilitating co-design sessions with community-level stakeholders.

- Experience ensuring best ethical practices, including management of informed consent, information sharing, data protection, confidentiality, and anonymity, including completion of a recognised Good Clinical Practice “GCP” training course.

- Experience in quality assurance of qualitative data, including transcript review and translation verification.

- Understanding of the local context and demonstrated cultural sensitivity.

- Willingness to travel for fieldwork and work flexible hours where required.

- Experience working with malaria stakeholders, including government, implementing partners, and community-level actors (desirable).

- Master's degree in public health, social sciences, or a related field (desirable).

TOTAL NUMBER OF CONTRACT DAYS (ALL CONSULTANTS COMBINED): 42.

Duration:	Within three (3) months

Period:		14th September 2026 to 30th November 2026

Deliverables:

| Deliverable | Activities | Output | No. Of Days | Timeframe |
| --- | --- | --- | --- | --- |
| Component 2: Qualitative Feasibility and Acceptability Inquiry completed and report available | Conduct KIIs and FGDs, manage consent processes, oversee transcription/translation, conduct thematic analysis | Feasibility and acceptability assessment findings report, including barriers and and enablers for differentiated SMC delivery models | 32 | Sept–Oct 2026 |
| Component 3: rapid human centered design completed with a report shared | Organise and facilitate human centered design with caregivers and community distributors, analyse findings, define minimum viable support package | Behavioural design exploration findings report, including minimum viable support packages for differentiated SMC delivery models | 10 | Oct-Nov 2026 |